As our MVP is essentially a next-gen powered air-purifying respirator (PAPR)-style device with integrated ozone sterilization and downstream ozone scrubbing — a meaningful evolution for infection control in clinical and high-risk environments.

Building a domestic manufacturing facility (U.S.-based, say in California or Nevada) capable of producing this type of device will be complex due to:

- Regulatory compliance (FDA, OSHA, EPA)

- Medical-grade materials

- Embedded electronics (ozone generator, sensors)

- Cleanroom or controlled assembly environment

Below is a breakdown of the realistic 12-month cost and timeline to establish initial production capacity, including low-rate manufacturing (not full-scale mass production yet).

🧾 Realistic Cost to Establish a Manufacturing Facility (12-Month Horizon)

| Category | Estimated Cost (USD) |
| --- | --- |
| 1. Facility Lease or Buildout (10,000–20,000 sq ft) | $500,000 – $1,200,000 |
| 2. Cleanroom & Controlled Environment Setup | $300,000 – $600,000 |
| 3. Manufacturing Equipment | $800,000 – $1,500,000 |
| 4. Tooling, Molds, Fixtures | $250,000 – $500,000 |
| 5. Regulatory Compliance & Testing Infrastructure | $400,000 – $800,000 |
| 6. Labor & Training (Year 1) | $600,000 – $1,000,000 |
| 7. Quality Systems & ERP Setup | $200,000 – $400,000 |
| 8. Working Capital (Materials, Inventory) | $300,000 – $700,000 |
| 9. Utilities, HVAC, Ozone Safety Controls | $200,000 – $400,000 |
| TOTAL (Year 1 Estimate) | $3.55M – $7.1M |

🗓️ Realistic Timeline: From Groundwork to Production Readiness

| Phase | Duration | Key Activities |
| --- | --- | --- |
| 1. Site Selection & Lease | Month 1–2 | Secure zoning, EPA compliance, power access |
| 2. Facility Design & Buildout | Month 2–6 | Build clean areas, ozone safety systems |
| 3. Equipment Procurement | Month 3–6 | Long-lead items: molding machines, assembly lines |
| 4. Team Hiring & Training | Month 5–8 | Manufacturing engineers, QA, supervisors |
| 5. Regulatory Test Prep | Month 6–9 | Ozone emission testing, ISO 13485 setup, FDA prep |
| 6. Pilot Production | Month 9–12 | Start small batch runs, quality checks, validation |
| 7. Full Low-Rate Production | Month 12+ | Begin limited commercial runs, prepare for scale |

🔧 Notable Technical & Regulatory Considerations

1. Ozone Handling & Emissions

- You will need indoor ozone monitoring systems, emergency shutdown protocols, and potentially EPA reporting.

- OSHA limits ozone exposure to 0.1 ppm over 8 hours, so the design must demonstrate containment and neutralization (which your activated carbon filter helps with).

- May require independent lab validation of ozone scrubbing efficacy post-carbon filter.

2. FDA Regulatory Classification

- This will likely be a Class II device due to active sterilization features and patient proximity.

- You’ll need 510(k) clearance, meaning bench testing, biocompatibility, emissions data, and real-world simulations.

3. Cleanroom Assembly for Filters & Mask Components

- PAPR-style masks require strict assembly protocols, especially for:

  - Filter sealing

  - Flow path control

  - Electronics (e.g., for ozone generation and battery packs)

🏭 Example Cities with Manufacturing Viability

| Location | Rationale |
| --- | --- |
| Nevada (e.g., Reno) | Lower cost, business-friendly, industrial parks |
| Texas (e.g., Austin) | Medtech cluster, good talent pool |
| Arizona (e.g., Phoenix) | Clean energy grid, open land, less red tape |
| California (Central Valley) | Access to medtech talent, higher cost, but regulatory familiarity |

✅ Summary

| Item | Estimate |
| --- | --- |
| 12-month total setup cost | $3.5M – $7.1M |
| Facility launch timeframe | ~12 months |
| Production output (pilot) | 2,000–10,000 units/month depending on automation level |
| Regulatory runway | FDA 510(k): ~9–15 months depending on pre-sub pathway |