## Cash Flow
Month | Facility Lease/Buildout | Cleanroom Setup | Equipment Procurement | Tooling & Fixtures | Regulatory & Testing | Labor & Training | Quality & ERP Systems | Working Capital | Utilities & Ozone Safety | Total Monthly Spend
Month 1 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
Month 2 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
Month 3 | 100000 | 100000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 350000
Month 4 | 0 | 100000 | 150000 | 0 | 0 | 0 | 66666 | 0 | 0 | 316666
Month 5 | 0 | 0 | 150000 | 50000 | 0 | 83333 | 66666 | 0 | 66666 | 416665
Month 6 | 0 | 0 | 150000 | 50000 | 66666 | 83333 | 66666 | 0 | 66666 | 483331
Month 7 | 0 | 0 | 0 | 0 | 66666 | 83333 | 0 | 0 | 66666 | 216665
Month 8 | 0 | 0 | 0 | 0 | 66666 | 83333 | 0 | 70000 | 0 | 219999
Month 9 | 0 | 0 | 0 | 0 | 0 | 83333 | 0 | 70000 | 0 | 153333
Month 10 | 0 | 0 | 0 | 0 | 0 | 83333 | 0 | 70000 | 0 | 153333
Month 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Month 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Org Chart
Role | FTE
VP of Manufacturing | 1
Quality Assurance Manager | 1
Regulatory Affairs Lead | 1
Production Supervisor | 1
Manufacturing Engineers (2) | 2
Assembler Technicians (6) | 6
Supply Chain Manager | 1
Facilities & Maintenance | 1
HR/Admin Support | 1

## Project Plan
Task | Start Month | Duration (months)
Site Selection & Lease | 1 | 2
Facility Design & Buildout | 2 | 4
Cleanroom Installation | 2 | 3
Equipment Procurement | 3 | 4
Tooling & Fixtures | 5 | 2
Regulatory Setup | 6 | 3
Hiring & Training | 5 | 4
ERP & Quality Systems | 4 | 3
Pilot Production Start | 9 | 4